## Tracker
Process Improvement Prioritization List
| Submitter | Date | Pain Point | Type of Pain | Ease to Fix | Magnitude of Issue | Status
| J. Doe | 2024-09-12 | Manual data entry required for weekly payment emails | Not Scalable | 1. Easy | 2. Medium | 1. Open
Instructions
| (1) | Download and add fields if appropriate for your team.
|  | • | Possible fields to include could be: sub-department; name of process (ie, payroll, billing, etc); estimated cost (external or internal costs)
| (2) | Introduce process improvement initiative to your team
|  | • | If appropriate, share article: | Getting Started with Process Improvements
| (3) | Distribute about 4 weeks before your planning and OKR cycle. Set a deadline for contributions for 1-2 weeks from distribution date
|  | • | If possible, provide shared access (such as a Google sheet or Shared Excel) to create a single consolidated list
|  | • | Check in with team 4-8 business days, particularly with team members who haven't added any paid points
| (4) | Sort list by "Ease to Fix", then by "Magnitude of Issue". Sort each from 1 to 3
| (5) | Discuss all "Easy / Large" and "Easy / Medium" items with entire team. Potential questions:
|  | • | How were assumptions on size and ease of solution made?
|  | • | Do you think the solutions are achievable without new tools or investments?
|  | • | Who else is being impacted by that pain point?
|  | • | If you fix one problem now, does it make it easier or harder to fix the next one later?
| (6) | Select NO MORE THAN TWO to prioritize and build into OKRs for this period
|  | • | The remaining pain points can get revisited and re-prioritized next period

## Drop Down Menus
Type of Pain | Ease to Fix | Magnitude of Issue | Status
Error Prone | 1. Easy | 1. Large | 1. Open
Not Scalable | 2. Medium | 2. Medium | 2. Active
I Just Hate Doing This | 3. Difficult | 3. Small | 3. Resolved